TriageAI

Confidence-Aware Support Ticket Classification with Human-in-the-Loop Routing

Project Planning & Management Document

| Item | Details |
| --- | --- |
| Project title | TriageAI: Confidence-Aware Support Ticket Classification with Human-in-the-Loop Routing |
| Domain | Artificial Intelligence, Machine Learning, Natural Language Processing |
| Project type | AI/ML application (prototype) |
| Team size | 6 members |
| Team leader | Abanoub Ehab Refaat Labib |
| Document date | October 13, 2026 |
| Version | 1.0 (planning 3 first phases) |
| Official delivery date | December 4, 2026 |

# 1. Project Proposal

## 1.1 Project Overview

Customer support teams receive large volumes of tickets every day, covering technical issues, billing and payments, product problems, returns, and general requests. Reading each ticket and assigning it to the right department by hand is slow and can be inconsistent.

TriageAI is an intelligent ticket classification and routing system. It uses Natural Language Processing (NLP) and Machine Learning (ML) to analyze a customer message and predict the most appropriate support department (queue).

Unlike a basic classifier, TriageAI is confidence-aware. It checks how confident the model is before deciding whether to recommend automatic routing or to send the ticket to a human reviewer. When a prediction does not meet the selected confidence threshold, the ticket is flagged for human review instead of being accepted automatically. For uncertain tickets the system can also show the reviewer the top two candidate departments.

The project evaluates traditional text classification models, analyzes their errors, and tracks all experiments with MLflow. An interactive interface may be built to demonstrate the system.

## 1.2 Problem Statement

Ticket assignment normally requires an employee to read and interpret each message. This becomes inefficient as ticket volume grows. Assigning tickets automatically without considering how reliable the prediction is can also send tickets to the wrong department.

There is therefore a need for a system that can:

- Automatically classify incoming support tickets.

- Identify the most appropriate support department.

- Evaluate prediction confidence before recommending automatic routing.

- Flag uncertain predictions for human review.

- Provide measurable results that show how reliable the system is.

## 1.3 Project Objectives

- Develop an NLP-based system that classifies customer support tickets into predefined departments.

- Explore and preprocess the selected dataset to understand its structure, quality, and class distribution.

- Implement TF-IDF and evaluate traditional ML models, including Multinomial Naive Bayes and Logistic Regression.

- Compare candidate models using appropriate classification metrics, with particular attention to Macro F1-score.

- Analyze misclassified tickets and investigate the effect of class imbalance.

- Implement confidence-aware routing that separates predictions eligible for automatic routing from those requiring human review.

- Evaluate the trade-off between automatic routing coverage and routing errors.

- Use MLflow to track experiments, parameters, metrics, and candidate models.

- Develop an interactive demonstration interface if time permits after the core system is complete.

- Produce clear technical documentation of the methodology, experiments, limitations, and results.

## 1.4 Dataset Description

The project uses the Customer IT Support - Ticket Dataset by Tobias Bueck (Softoft), published on Kaggle under the CC BY 4.0 license. The main file is aa_dataset-tickets-multi-lang-5-2-50-version.csv. The dataset page states that the data was synthetically generated and may not reflect real-world data. This is an important limitation and is documented throughout the project.

Initial inspection of the file showed:

| Property | Finding |
| --- | --- |
| Total records / columns | 28,587 rows, 16 columns |
| Languages | English (16,338 rows) and German (12,249 rows) |
| Input text | subject + body, joined into one text field (missing subject values, about 13% of rows, are replaced with an empty string; body has no missing values) |
| Target | queue (10 support departments, no missing values) |
| English subset quality | 0 duplicate texts, 0 texts with conflicting labels; average text length about 59 words (maximum 172); about 0.34% of English texts contain German characters |
| Excluded fields | answer (written after the ticket is handled, so using it would leak information); type, priority, and tag_1-tag_8 (assigned after the ticket is reviewed); version (irrelevant) |

Queue distribution of the English subset (the working dataset):

| Queue (class) | Tickets | Share | Approx. in test set (15%) |
| --- | --- | --- | --- |
| Technical Support | 4,737 | 29.0% | ~711 |
| Product Support | 3,073 | 18.8% | ~461 |
| Customer Service | 2,410 | 14.8% | ~362 |
| IT Support | 1,942 | 11.9% | ~291 |
| Billing and Payments | 1,595 | 9.8% | ~239 |
| Returns and Exchanges | 820 | 5.0% | ~123 |
| Service Outages and Maintenance | 664 | 4.1% | ~100 |
| Sales and Pre-Sales | 513 | 3.1% | ~77 |
| Human Resources | 348 | 2.1% | ~52 |
| General Inquiry | 236 | 1.4% | ~35 |
| Total | 16,338 | 100% | ~2,451 |

Key observations and implications

- Class imbalance is real and large. The largest class is about 20 times the size of the smallest. Accuracy alone would be misleading, so Macro F1-score and per-class recall are the primary metrics.

- Small classes give unstable test numbers. General Inquiry has only about 35 test tickets, so one ticket changes its recall by about 3 percentage points. Per-class results for small classes will be reported with this caveat, and cross-validation will be used to support them.

- Labels may be noisy. A quick look at a small sample suggested some tickets whose text does not clearly match their queue, and several queues overlap in meaning (Technical Support, IT Support, Product Support). This will be checked during EDA and error analysis. Part of the model's errors may come from the labels, not the model.

- Synthetic text. The tickets share a similar writing style. Results may be better than on real tickets and should not be presented as real-world performance.

- English only. The initial version uses English tickets, because stop-word lists, lemmatization, and distilbert-base-uncased (optional extension) are English-specific. German tickets are left for future work.

## 1.5 Project Scope

### In scope

- Dataset loading and validation, and exploratory data analysis (EDA).

- Missing-value and text-quality investigation; English subset selection.

- Text preprocessing and cleaning (case normalization, regex cleaning, tokenization, stop-word handling, stemming or lemmatization).

- Text representation: Bag of Words, N-grams, and TF-IDF.

- Multinomial Naive Bayes and Logistic Regression models, with and without class weighting.

- Evaluation with Accuracy, Precision, Recall, F1-score, Macro F1-score, and confusion matrix; misclassification analysis; most informative features.

- Confidence-aware routing with a validated threshold, top-2 suggestions, and human-review recommendation.

- Evaluation of automatic routing coverage and routing errors.

- MLflow experiment tracking, technical documentation, and project demonstration.

### Out of scope for the initial version

- Training a large language model from scratch.

- Building a production-scale support platform or integrating with real ticketing systems, email, or messaging services.

- Processing scanned documents or performing OCR.

- Multilingual classification (German and other languages).

- Automatically sending responses to customers.

- Guaranteeing that high-confidence predictions are always correct.

Optional extensions after the core system is complete: a pretrained Transformer (Hugging Face) compared against the TF-IDF baseline, probability calibration with CalibratedClassifierCV, label-noise analysis with cleanlab, Explainable AI (SHAP or LIME), and a monitoring plan.

## 1.6 Expected Deliverables

The planned deliverables are listed with owners and due dates in Section 2.8. These are planned deliverables, not completed results.

# 2. Project Plan

## 2.1 Development Approach

The project follows an incremental approach. The team first builds a reliable classification baseline, then adds confidence-aware routing on top of it. Each stage produces a measurable deliverable that is reviewed before the next stage begins. The stages are:

- Project planning and requirements definition.

- Literature review and technical research.

- System analysis and design.

- Data preparation and exploratory analysis.

- Baseline model development.

- Model evaluation and error analysis.

- Confidence-aware routing implementation.

- MLflow tracking and reproducibility checks (logging starts with the first experiment).

- Interface development and system testing.

- Documentation and final presentation.

## 2.2 Timeline and Official Deadlines

| Phase | Planned activities | Official deadline |
| --- | --- | --- |
| Planning, Literature Review, and Requirements Gathering | Proposal, project plan, research, requirements, initial documentation | October 16, 2026 |
| System Analysis and Design | Architecture, workflow, use cases, component design, system specifications | November 6, 2026 |
| Implementation | Data pipeline, model training, evaluation, confidence-aware routing, integration | November 30, 2026 |
| Final Presentation, Testing, and Reports | Final testing, documentation, presentation, demonstration | December 4, 2026 |

## 2.3 Project Gantt Chart

The chart shows the four project phases, the tasks inside each phase, and the four official milestones (red markers). The hatched bar is an optional task. Dates follow the detailed schedule in Section 2.4.

## 2.4 Detailed Work Schedule

This is the internal development plan. Activities may overlap when appropriate. MLflow logging starts with the first model experiment (November 7) rather than at the end, so no run is lost.

| Period | Activities | Expected output |
| --- | --- | --- |
| Oct 13-16 | Finalize the proposal, project plan, literature review, and requirements | Initial documentation package |
| Oct 17-23 | Review related research, inspect the dataset, finalize the system design | Literature review and design specification |
| Oct 24-30 | Perform EDA, investigate data quality, build the preprocessing pipeline | EDA report and prepared data pipeline |
| Oct 31-Nov 6 | Define the architecture, modeling workflow, routing logic, and interface requirements | Completed system analysis and design |
| Nov 7-13 | Implement TF-IDF and baseline models; start MLflow logging from the first run | Initial trained models, first tracked runs |
| Nov 14-19 | Compare models, evaluate class-level performance, analyze errors | Model evaluation report |
| Nov 20-24 | Implement and evaluate confidence-aware routing | Routing component and evaluation results |
| Nov 25-27 | Review and organize MLflow experiments; build the demo interface if feasible | Tracked experiments and prototype |
| Nov 28-30 | Integrate components, resolve defects, complete implementation | Integrated system and code |
| Dec 1-3 | Final testing, documentation, presentation rehearsal | Final report and presentation |
| Dec 4 | Deliver the final presentation and submission | Final project deliverables |

## 2.5 Task Dependencies and Critical Path

| Task | Depends on | Output used by |
| --- | --- | --- |
| Dataset inspection and design | Approved proposal | EDA, preprocessing, architecture |
| EDA and preprocessing pipeline | Dataset inspection | Feature extraction, all models |
| TF-IDF features and baseline models | Preprocessing pipeline | Model comparison |
| Model comparison and error analysis | Trained baseline models | Choice of model for routing |
| Confidence-aware routing | Selected model with probability output | Integration, demo interface |
| MLflow tracking | First model run (logging starts Nov 7) | Model comparison, reproducibility check |
| Demo interface (optional) | Routing component | Final presentation |
| Integration and bug fixing | Routing, MLflow | Final testing |
| Final testing and documentation | Integrated system | Final presentation |

Critical path: dataset inspection, EDA and preprocessing, baseline models, model comparison, confidence-aware routing, integration, final testing, final presentation. A delay in any of these moves the final date. The demo interface is not on the critical path and is dropped first if time runs short.

## 2.6 Work Breakdown Structure (WBS)

Owners are proposed and will be confirmed at the System Design milestone (November 6).

| WBS | Work package | Proposed owner | Output |
| --- | --- | --- | --- |
| 1 | Project management |  |  |
| 1.1 | Proposal and project plan | Abanoub, Youssef | Planning document |
| 1.2 | Risk register and KPIs | Youssef | Risk and KPI tables |
| 1.3 | Progress tracking and integration | Abanoub | Weekly status |
| 2 | Research and requirements |  |  |
| 2.1 | Literature review | Farah, Ahmed Fares | Review and references |
| 2.2 | Stakeholders and use cases | Ahmed Ashraf | Use-case document |
| 2.3 | Requirements specification | Sama | Functional and non-functional requirements |
| 3 | System design |  |  |
| 3.1 | Architecture and workflow | Abanoub, Ahmed Fares | Design document |
| 3.2 | Data and evaluation design | Farah, Ahmed Fares | Evaluation protocol |
| 3.3 | Routing logic and interface design | Abanoub, Ahmed Ashraf | Routing and interface specification |
| 4 | Data preparation |  |  |
| 4.1 | Loading, validation, EDA | Farah | EDA report |
| 4.2 | Preprocessing pipeline | Farah | Reusable preprocessing code |
| 5 | Modeling and evaluation |  |  |
| 5.1 | TF-IDF, Bag of Words, N-grams | Ahmed Fares | Feature pipeline |
| 5.2 | Naive Bayes and Logistic Regression | Ahmed Fares | Trained models |
| 5.3 | Model comparison and error analysis | Ahmed Fares, Sama | Evaluation report |
| 6 | Confidence-aware routing |  |  |
| 6.1 | Probability output and threshold selection (validation set) | Abanoub | Selected threshold |
| 6.2 | Coverage and error evaluation (test set); top-2 accuracy | Abanoub | Routing evaluation |
| 6.3 | Calibration diagnostics (if time permits) | Abanoub, Ahmed Fares | Reliability diagram |
| 7 | Tracking and demonstration |  |  |
| 7.1 | MLflow experiment tracking | Youssef | Experiment records |
| 7.2 | Streamlit demo (optional) | Ahmed Ashraf | Interactive prototype |
| 8 | Testing and delivery |  |  |
| 8.1 | Test cases and system testing | Sama | Test report |
| 8.2 | Final report and presentation | All members | Report and slides |

## 2.7 Milestones and Acceptance Criteria

### Milestone 1: Planning Completion (deadline: October 16, 2026)

- Project proposal completed; scope and objectives documented.

- Project timeline and Gantt chart established.

- Team responsibilities assigned.

- Initial risks and KPIs defined.

- Requirements and research tasks documented.

### Milestone 2: System Design Completion (deadline: November 6, 2026)

- Dataset and input/output specifications documented.

- System architecture defined; classification and routing workflows designed.

- Model evaluation methodology established.

- Functional and non-functional requirements documented.

### Milestone 3: Implementation Completion (deadline: November 30, 2026)

- At least one classification model trained and evaluated; candidate models compared when implementation permits.

- Confidence-aware routing implemented; routing coverage and errors measured.

- MLflow experiment tracking integrated.

- Core components tested and documented.

### Milestone 4: Final Delivery (deadline: December 4, 2026)

- Final system tested; evaluation results and known limitations documented.

- Final presentation completed.

- Code and documentation organized in the project repository.

## 2.8 Deliverables, Owners, and Due Dates

| # | Deliverable | Proposed owner | Due |
| --- | --- | --- | --- |
| 1 | Project proposal, plan, risk register, and KPIs (this document) | Abanoub, Youssef | Oct 16 |
| 2 | Literature review and references | Farah, Ahmed Fares | Oct 23 |
| 3 | Stakeholder analysis, use cases, and requirements specification | Ahmed Ashraf, Sama | Nov 6 |
| 4 | System design document | Abanoub, Ahmed Fares | Nov 6 |
| 5 | Cleaned dataset preparation pipeline and EDA report | Farah | Oct 30 |
| 6 | Reproducible preprocessing and feature extraction pipeline | Farah, Ahmed Fares | Nov 13 |
| 7 | Trained baseline models | Ahmed Fares | Nov 13 |
| 8 | Model comparison, evaluation, and error analysis report | Ahmed Fares, Sama | Nov 19 |
| 9 | Confidence-aware routing component and its evaluation | Abanoub | Nov 24 |
| 10 | MLflow experiment records | Youssef | Nov 27 |
| 11 | Interactive demonstration (optional) | Ahmed Ashraf | Nov 27 |
| 12 | GitHub repository with code and README | Abanoub | Nov 30 |
| 13 | Final technical report and presentation | All members | Dec 3-4 |

These are planned deliverables, not completed results.

## 2.9 Evaluation Protocol

The following rules keep the evaluation honest and prevent data leakage:

- Split: 70% train, 15% validation, 15% test, stratified by queue, fixed random seed (42). The test set is used once, for the final report.

- Pipelines: preprocessing, vectorizer, and classifier are combined in one scikit-learn Pipeline, so learned steps (such as the TF-IDF vocabulary) are fitted on training data only.

- Model selection: models are compared on the validation set using Macro F1-score, with per-class precision and recall and the confusion matrix. Class weighting (class_weight="balanced") is compared against no weighting.

- Stability: stratified 5-fold cross-validation is used alongside the test set, because small classes have few test tickets.

- Routing threshold: selected on the validation set only, using a clear target (for example, the lowest threshold that reaches a chosen accuracy on automatically routed tickets). Final coverage and error are then reported on the test set.

- Calibration (if time permits): reliability diagram and Expected Calibration Error, comparing probabilities before and after calibration. Calibration is fitted with cross-validation on the training data, not on the data used to choose the threshold.

- Honest reporting: results are reported as measured, including when coverage at the target accuracy is lower than hoped.

## 2.10 Resource Allocation

| Resource | Planned use |
| --- | --- |
| Python | Main programming language |
| Pandas and NumPy | Data manipulation and analysis |
| Matplotlib and Seaborn | EDA and visualization |
| Scikit-learn (and NLTK or spaCy) | Text processing, model training, and evaluation |
| MLflow | Experiment tracking and model comparison |
| Jupyter Notebook | Exploration and experimentation |
| Git and GitHub | Version control and team collaboration |
| Streamlit | Optional interactive demonstration |
| Existing team computers | Development and testing; no dedicated GPU required for the baseline models |
| Human resources | 6 team members, about 7 weeks (October 13 to December 4, 2026) |
| Budget | No direct cost: open-source software, a public dataset, and existing hardware |

## 2.11 Assumptions and Constraints

### Assumptions

- The dataset remains available on Kaggle and can be downloaded and stored locally (the dataset version used is recorded).

- The queue column is the reference label for each ticket, even though it may contain some noise.

- Each team member can contribute regularly during the 7 weeks.

- Traditional ML models run on ordinary laptops.

### Constraints

- Fixed official deadlines (October 16, November 6, November 30, December 4, 2026).

- Small team with other course workload; optional features must not delay core deliverables.

- Synthetic English-language data limits how far the results can be generalized to real support systems.

- No access to a real company ticketing system or real customer data.

## 2.12 Communication Plan

| Activity | Frequency | Participants | Purpose |
| --- | --- | --- | --- |
| Team progress meeting | Weekly (day and time agreed by the team) | All members | Completed and outstanding tasks, blockers, decisions |
| Short status update in the team chat | Twice a week | All members | Early warning of delays |
| GitHub issues and project board | Continuous | All members | Task ownership and status |
| Code review (pull requests) | For every merge | Author and one reviewer | Quality and consistency |
| Milestone review | Before each official deadline | All members | Check acceptance criteria and risks |
| Escalation | As needed | Team leader | Resolve conflicts and scope questions |

# 3. Task Assignment and Team Roles

The project team has six members. Each member has a primary responsibility, and all members take part in reviewing the project.

## 3.1 Planning-Phase Responsibilities

| Team member | Primary responsibility | Assigned tasks |
| --- | --- | --- |
| Abanoub Ehab Refaat Labib | Team Leader and Project Coordinator | Coordinate the team, prepare and review the proposal, monitor progress, resolve issues, keep deliverables consistent |
| Youssef Ashraf | Project Planning and Management | Detailed timeline, milestones, resource allocation, risk register, KPI definitions |
| Farah Hany | Literature Review Research | Find relevant research on NLP, ticket classification, text representations, and classification models |
| Ahmed Fares | Literature Synthesis and References | Summarize findings, organize references, compare approaches, support technical decisions |
| Ahmed Ashraf | Stakeholder Analysis and Use Cases | Identify stakeholders, user stories, use cases, and expected interaction with the system |
| Sama Ahmed | Requirements Engineering | Functional and non-functional requirements, system inputs and outputs, requirements specification |

## 3.2 Proposed Implementation-Phase Roles

These roles are proposed so that every member has a clear technical task. They will be confirmed at the System Design milestone and can be adjusted by the team leader.

| Team member | Implementation role | Main tasks |
| --- | --- | --- |
| Abanoub Ehab Refaat Labib | Integration and routing lead | Confidence-aware routing, threshold selection, repository owner, final integration |
| Youssef Ashraf | Experiment tracking and reproducibility | MLflow setup and logging, run comparison, environment and seed documentation |
| Farah Hany | Data and preprocessing | Dataset loading, EDA, cleaning, preprocessing pipeline |
| Ahmed Fares | Modeling and evaluation | TF-IDF, Naive Bayes, Logistic Regression, model comparison, most informative features |
| Ahmed Ashraf | Interface and use cases | Streamlit demo (optional), alignment of the demo with the use cases |
| Sama Ahmed | Testing and error analysis | Test cases, error analysis of misclassified tickets, requirements traceability |

## 3.3 RACI Matrix

R = Responsible, A = Accountable, C = Consulted, I = Informed. Abanoub (team leader) is accountable for all deliverables.

| Activity | Abanoub | Youssef | Farah | Ahmed F. | Ahmed A. | Sama |
| --- | --- | --- | --- | --- | --- | --- |
| Proposal and project plan | A | R | C | C | C | C |
| Literature review | A | I | R | R | C | I |
| Stakeholders and use cases | A | I | I | I | R | C |
| Requirements specification | A | I | I | I | C | R |
| EDA and preprocessing | A | I | R | C | I | C |
| Model training and comparison | A | I | C | R | I | C |
| Confidence-aware routing | A/R | I | C | C | I | C |
| MLflow tracking | A | R | I | C | I | I |
| Demo interface (optional) | A | I | I | C | R | C |
| Testing and error analysis | A | I | C | C | C | R |
| Final report and presentation | A/R | R | R | R | R | R |

## 3.4 Shared Responsibilities

- Reviewing the project scope and feasibility, and validating technical assumptions.

- Reviewing the dataset and evaluation plan.

- Testing the implemented system.

- Preparing the final report and contributing to the final presentation.

## 3.5 Project Management

The team leader monitors progress against the milestones. The team keeps a shared repository and documented task assignments to avoid duplicated work. Progress reviews cover completed tasks, outstanding tasks, technical blockers, risks to upcoming deadlines, and decisions that need team agreement. Scope changes are judged against the available time and the priority of the core deliverables.

# 4. Risk Assessment and Mitigation Plan

Risk management aims to find problems early and prepare practical responses. Ratings are initial qualitative estimates and will be reviewed at each milestone. Score = Probability x Impact (Low = 1, Medium = 2, High = 3). Owners are proposed.

## 4.1 Risk Register

| ID | Risk | Prob. | Impact | Score | Owner | Mitigation | Contingency |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Class imbalance reduces performance on small departments | High | High | 9 | Ahmed Fares | Stratified split, report Macro F1 and per-class metrics, compare class weighting | Merge or review the weakest classes; report limitation |
| R2 | Text preprocessing removes useful information | Medium | High | 6 | Farah | Start with a simple baseline, compare preprocessing options, inspect errors | Fall back to minimal preprocessing |
| R3 | Data leakage gives misleading results | Medium | High | 6 | Farah | Split before fitting; use sklearn Pipelines; exclude answer, tags, type, priority | Re-run experiments after fixing the pipeline |
| R4 | Model performance is inadequate for some departments | Medium | High | 6 | Ahmed Fares | Compare models, inspect the confusion matrix, analyze errors | Report limits honestly; try n-grams or class weighting |
| R5 | Prediction confidence does not match actual correctness | Medium | High | 6 | Abanoub | Evaluate routing errors; check calibration; choose threshold on validation data | Use calibrated probabilities or a margin rule (gap between top two) |
| R6 | Automatic routing coverage is too low at acceptable error | Medium | Medium | 4 | Abanoub | Compare several thresholds; report the coverage-error trade-off | Choose a lower accuracy target and state it clearly |
| R7 | Too much time spent on optional features | High | High | 9 | Abanoub | Finish classification, evaluation, and routing first; fix a cut-off date for extras | Drop the demo and extensions |
| R8 | Team coordination delays work | Medium | High | 6 | Youssef | Task owners, internal deadlines, weekly reviews, regular integration | Leader reassigns tasks |
| R9 | Synthetic data and label noise limit performance and generalization | High | Medium | 6 | Sama | Validate labels, inspect samples, state the data is synthetic in all reports | Optional small real-data check if time permits |
| R10 | Experiments cannot be reproduced | Medium | Medium | 4 | Youssef | Fixed seeds, MLflow logging, package versions in requirements file | Re-run from saved configuration |
| R11 | Demo interface fails during the presentation | Medium | Medium | 4 | Ahmed Ashraf | Treat the interface as secondary; test early | Tested notebook demo as backup |
| R12 | Not enough time for final testing and documentation | Medium | High | 6 | Youssef | Reserve the last days for integration, testing, and rehearsal | Cut optional work to protect testing |
| R13 | Dataset becomes unavailable or changes version | Low | Medium | 2 | Youssef | Keep a local copy and record the dataset version | Use the stored copy |

## 4.2 Risk Heat Map

| Probability \ Impact | Low | Medium | High |
| --- | --- | --- | --- |
| High |  | R9 | R1, R7 |
| Medium |  | R6, R10, R11 | R2, R3, R4, R5, R8, R12 |
| Low |  | R13 |  |

## 4.3 Risk Prioritization

The highest-priority risks are:

- Class imbalance and weak performance on small departments (R1).

- Scope growth and missed deadlines caused by optional features (R7).

- Synthetic data and label noise limiting performance and generalization (R9).

- Data leakage and unreliable evaluation (R3).

- Confidence that does not match correctness, or too many routing errors (R5, R6).

These risks are reviewed at every major milestone. The team prefers a reliable, evaluated core system over adding features that cannot be tested properly.

# 5. Key Performance Indicators (KPIs)

KPIs measure the model, the confidence-aware routing mechanism, the system prototype, and the project delivery. Targets are provisional planning targets, not claims about current performance.

## 5.1 Model Performance KPIs

| KPI | Definition | Target or evaluation rule |
| --- | --- | --- |
| Macro F1-score | Average F1 across classes, each class weighted equally | Primary model-selection metric; establish a baseline, then seek improvement |
| Weighted F1-score | F1 averaged by class size | Report alongside Macro F1 |
| Accuracy | Share of correctly classified tickets | Report, but never as the only metric |
| Per-class precision and recall | Correctness of predictions for a class, and share of the class found | Report for every department |
| Confusion matrix | Which departments are confused with each other | Inspect and discuss the main confusions |
| Top-2 accuracy | Share of tickets whose true department is among the two most likely predictions | Report; supports showing two candidates to the reviewer |

Macro F1 is the primary metric because the departments differ greatly in size and accuracy alone could hide weak results on small classes. No final performance threshold is claimed until baseline experiments are complete.

## 5.2 Confidence-Aware Routing KPIs

| KPI | Definition | Evaluation method |
| --- | --- | --- |
| Automatic routing coverage | Share of tickets whose highest predicted probability meets the threshold | Measure at several thresholds |
| Automatic routing error rate | Share of automatically routed tickets sent to the wrong department | Compare with ground-truth labels |
| Human review rate | Share of tickets below the threshold (sent to a person) | Calculate for each threshold |
| Coverage-error trade-off | Relationship between coverage and error rate | Coverage-vs-accuracy curve; choose an operating point |
| Probability calibration | Agreement between predicted confidence and observed correctness | Reliability diagram and Expected Calibration Error, when feasible |

Thresholds are selected on validation data, and final routing performance is reported on a separate test set. A ticket is automatically routable when its highest predicted probability meets the threshold. This is a decision rule, not a guarantee that the prediction is correct. Some model probabilities (for example Naive Bayes) are often poorly calibrated, so calibration is checked before trusting the confidence values.

## 5.3 System Performance KPIs

| KPI | Definition | Evaluation method / target |
| --- | --- | --- |
| Response time (prediction latency) | Time to process a ticket and return the prediction and routing decision | Measure on development hardware; provisional target: under 1 second per ticket |
| Pipeline reliability | Handling of valid, empty, and invalid inputs | Test representative valid and invalid cases |
| Reproducibility | Ability to repeat an experiment from recorded settings | Verify saved parameters, metrics, and artifacts in MLflow |
| Interface functionality | Interface accepts a ticket and shows prediction, confidence, and routing decision | Test the main flows if an interface is built |

## 5.4 Project Management KPIs

| KPI | Definition | Target |
| --- | --- | --- |
| Milestone completion | Share of milestones completed by their deadlines | All four official milestones on time |
| Deliverable completion | Share of required deliverables completed and reviewed | All required deliverables before final submission |
| Testing completion | Share of planned core test cases executed | Run and document all agreed core tests |
| Documentation completeness | Reports, setup instructions, methodology, and results are documented | All documents reviewed before delivery |

## 5.5 Alignment with Common Project KPIs

Typical project KPIs include response time, system uptime, and user adoption rate. Their treatment in this project:

| Common KPI | How it applies to TriageAI |
| --- | --- |
| Response time | Measured as prediction latency (Section 5.3). |
| System uptime | Not a primary KPI: the project is a prototype and is not deployed as a production service. Pipeline reliability (handling valid and invalid inputs) is used instead. |
| User adoption rate | Not measurable without real users. Instead, the team checks that the demo supports the documented use cases, and may collect informal feedback from classmates or instructors. |

# 6. Project Success Criteria

TriageAI is considered successful when the team can demonstrate that:

- A trained ML model classifies support tickets into the defined departments.

- Model performance is evaluated on a held-out test set with appropriate metrics.

- The system obtains prediction probabilities and applies a configurable confidence threshold.

- The routing component separates automatic-routing candidates from tickets that need human review.

- The team can quantify automatic routing coverage and routing errors.

- Experiments and results are documented and reproducible to a reasonable degree.

- The final report explains the methodology, findings, limitations (including the synthetic data), and future improvements.

- The project is delivered according to the official milestones.

The team will report measured results honestly, including cases where performance or routing coverage does not meet initial expectations.

# 7. Literature Review

## 7.1 Introduction

Customer support teams receive messages about technical faults, billing, products, outages, returns, and general requests. Reading each message and assigning it to a department by hand is slow and can be inconsistent (Section 1.2). Natural Language Processing (NLP) and Machine Learning (ML) offer ways to assign text to predefined categories automatically. A classifier should not be judged only by the fact that it produces a prediction, however. It is also important to understand its errors and to decide when a prediction can be accepted automatically and when a person should review it.

This section reviews the techniques that are relevant to TriageAI, explains why each one was selected or deferred, records the lecturer's initial feedback, lists suggested improvements, and proposes a checklist for the final grading criteria. It is a focused, applied review that supports the design decisions of this project. It is not a systematic survey, and it does not claim any experimental result in advance. Its findings feed the requirements in Section 8 and the evaluation protocol in Section 2.9.

## 7.2 Review of Related Techniques and Approaches

### 7.2.1 Text Classification

Text classification is a supervised learning task. A model learns from labeled examples how to assign a document to one of a fixed set of categories. In TriageAI the input is the ticket subject and body, and the target is the queue (department), which makes this a single-label, multiclass problem with ten classes. The scikit-learn documentation [1] and the scikit-learn library paper [2] describe the standard workflow that the project follows: convert text to numerical features, train a classifier, and evaluate it on held-out data.

Supervised learning is suitable here because the selected dataset already contains ticket text and queue labels. One caution applies: several queues overlap in meaning (Technical Support, IT Support, and Product Support; see Section 1.4). Some errors are therefore expected to come from ambiguous labels and not only from the model.

### 7.2.2 Text Representation: Bag of Words, N-grams, and TF-IDF

Machine learning algorithms need numerical input, so every ticket must be converted into a feature vector. Three related representations are relevant:

- Bag of Words (BoW): represents a document by how many times each word occurs.

- N-grams: extend BoW to sequences of consecutive words (for example "credit card" or "reset password"), which can capture short phrases that single words miss, at the cost of many more features.

- TF-IDF (Term Frequency, Inverse Document Frequency): weights each term by how often it appears in a document and by how rare it is across the collection, so words that appear in almost every ticket receive a lower weight [3], [4].

Words about payments or invoices may help to separate billing tickets from technical ones, but this has to be shown through evaluation and not assumed. TriageAI will use TF-IDF as the primary representation, and the validation set will be used to compare it with raw BoW counts and to compare unigrams against unigrams plus bigrams. Because n-grams increase the number of sparse features, settings such as min_df and max_features will be treated as tunable parameters.

The vectorizer (vocabulary and IDF values) must be fitted on training data only. Validation and test tickets are transformed with the already fitted vectorizer. This is enforced by placing preprocessing, vectorizer, and classifier in a single scikit-learn Pipeline (Section 2.9), which prevents data leakage.

### 7.2.3 Multinomial Naive Bayes

Multinomial Naive Bayes is a probabilistic classifier that is widely used for word-count features [4], [5]. It assumes that features are independent given the class. That assumption is rarely true for language, but the model is very fast to train and often gives a competitive baseline, which makes it a good first model for a team with a seven-week schedule.

A known weakness is relevant to this project. The independence assumption tends to make Naive Bayes probabilities extreme and poorly calibrated [6]. TriageAI makes routing decisions from predicted probabilities, so Naive Bayes will be kept as the baseline, but its confidence values will be checked (Section 7.2.7) before they are trusted. The project does not assume that Naive Bayes is the best or the worst model; this is decided by the experiments.

### 7.2.4 Logistic Regression

Despite its name, Logistic Regression is a classification model. In its multinomial form it produces one probability per class. Linear models work well on high-dimensional, sparse TF-IDF features, and a regularization parameter (C) controls overfitting. Empirical comparisons of supervised learners report that Logistic Regression usually gives better-behaved probabilities than Naive Bayes [6], although this is not guaranteed on any specific dataset.

In TriageAI, Logistic Regression is the main comparison model. It will be evaluated with and without class_weight="balanced" to see whether weighting helps the smaller queues. Its coefficients also provide the most informative terms for each queue, which supports error analysis (Section 1.5).

### 7.2.5 Traditional Models Compared with Transformer Models

Pretrained Transformer models such as BERT [7] and its smaller variant DistilBERT [8] often reach strong results on text classification because they use the context of each word. They also need more computing resources (a GPU is practically required for fine-tuning), take longer to train, and are harder to inspect.

The project plan therefore uses TF-IDF with Naive Bayes and Logistic Regression as the core, for four reasons: (1) it runs on ordinary laptops with no GPU (Section 2.10); (2) it trains quickly, so many experiments fit into the schedule; (3) it is easier to interpret; and (4) a strong, well-evaluated baseline is needed before anyone can judge whether a heavier model is worth its cost. Tickets in this dataset are short (about 59 words on average) and share a similar synthetic style, so a simple model may already perform well, and the benefit of a Transformer may be small. This is not assumed in either direction. A DistilBERT comparison remains an optional extension that starts only after the core system is complete.

### 7.2.6 Model Evaluation, Class Imbalance, and Stability

Classification should be evaluated with several metrics, because accuracy alone can hide poor results on small classes [9]. The project will use:

- Accuracy: the share of all tickets classified correctly.

- Precision and recall: for each class, the share of predictions that are correct, and the share of the class that is found.

- F1-score, Macro F1-score, and Weighted F1-score: the harmonic mean of precision and recall for each class, averaged with equal weight per class (Macro) or weighted by class size (Weighted).

- Top-2 accuracy: the share of tickets whose true queue is among the two most likely predictions, which supports showing two candidate queues to a reviewer.

- Confusion matrix: which queues are confused with each other.

The Phase 1 dataset analysis found 16,338 English tickets in ten queues. Technical Support has 4,737 tickets (29.0%) and General Inquiry has 236 (1.4%), a ratio of about 20 to 1. A model that always predicted Technical Support would reach about 29% accuracy while scoring very poorly on every other queue, so Macro F1-score and per-class recall are the primary metrics. A majority-class reference model (scikit-learn DummyClassifier) will be reported so that every result can be read against a trivial baseline.

Small classes also make test results unstable. General Inquiry has only about 35 test tickets, so a single ticket changes its recall by about three percentage points. For this reason the protocol adds stratified 5-fold cross-validation next to the held-out test set (Section 2.9).

### 7.2.7 Confidence, Calibration, and Selective Classification

A conventional classifier always returns a class. A classifier with a reject option can instead abstain on uncertain inputs. This idea is studied as selective classification [10], [11], [12], and it creates a trade-off between coverage (how many predictions are accepted) and the error rate among the accepted predictions. TriageAI applies this principle to ticket routing:

- The model predicts a queue and returns class probabilities.

- The system takes the probability of the predicted class as its confidence score.

- The score is compared with a configurable threshold.

- A prediction at or above the threshold is eligible for automatic routing.

- A prediction below the threshold is flagged for human review.

- For uncertain tickets, the top two candidate queues are shown to help the reviewer.

A predicted probability is not automatically a reliable estimate of correctness. Calibration measures how well predicted confidence matches observed accuracy, and it is commonly checked with reliability diagrams and Expected Calibration Error (ECE) [13]. Scikit-learn provides CalibratedClassifierCV to recalibrate probabilities [1]. A simple alternative confidence signal is the margin between the two highest probabilities, which is kept as a contingency in the risk register (R5, Section 4).

The threshold is an experimental parameter and not a fixed constant. It is selected on the validation set, using a stated target such as the lowest threshold that reaches a chosen accuracy on automatically routed tickets. The final behavior is then measured once on the test set. The metrics are automatic-routing coverage, the error rate among automatically routed tickets, and the human-review rate. A higher threshold is expected to reduce coverage and the error rate among accepted tickets, but the size of the effect must be measured and not assumed.

### 7.2.8 Label Noise and Error Analysis

The dataset is synthetic, and a quick inspection in Phase 1 suggested that some tickets do not clearly match their queue. When labels are noisy, part of the measured error belongs to the data and not to the model. Confident learning, implemented in the open-source cleanlab library, estimates which labels are likely wrong by using out-of-sample predicted probabilities [14]. In TriageAI, cleanlab is an optional extension. The core approach is to inspect the confusion matrix and a sample of misclassified tickets by hand, and to group the errors into patterns such as overlapping queues, ambiguous text, and very short tickets.

One rule applies to any label review: labels in the test set must not be changed in order to improve the reported score. Any label correction is applied to training data only and is documented.

### 7.2.9 Experiment Tracking and Reproducibility

Machine learning projects run many experiments with different models, text settings, and parameters. MLflow Tracking records parameters, metrics, and artifacts for each run so that runs can be compared and repeated [15]. TriageAI will start logging with the first model experiment (November 7, Section 2.4). Each run records the model type, TF-IDF settings (n-gram range, min_df, max_features), class-weight setting, regularization value, random seed, dataset version, validation Macro F1-score, and the per-class report and confusion matrix as artifacts. This gives a consistent record for a six-person team, which a set of notebook outputs does not.

## 7.3 Relevance of the Literature to TriageAI

The table summarizes how each technique is used in the project, with its status and the section of this document where it is planned.

| Technique | Purpose in TriageAI | Decision | Reference in this document |
| --- | --- | --- | --- |
| Text preprocessing | Prepare ticket subject and body for modeling | Core. Start simple and compare options (risk R2) | Sections 1.5, 4 |
| Bag of Words and N-grams | Alternative representations to compare | Core comparison on the validation set | Section 1.5 |
| TF-IDF | Convert text into numerical features | Core. Primary representation | Sections 1.5, 2.9 |
| Multinomial Naive Bayes | Fast baseline classifier | Core. Check its probabilities before use | Section 5.2 |
| Logistic Regression | Main comparison classifier with usable probabilities | Core. With and without class weighting | Section 1.5 |
| Macro F1 and per-class metrics | Fair comparison under class imbalance | Core. Primary model-selection metric | Sections 2.9, 5.1 |
| Stratified 5-fold cross-validation | Stabilize results for small classes | Core. Used next to the test set | Section 2.9 |
| Confidence threshold | Decide automatic routing or human review | Core. Selected on validation data | Section 5.2 |
| Top-2 candidates | Help the human reviewer | Should have. Top-2 accuracy is reported | Section 5.1 |
| Probability calibration | Check that confidence matches correctness | Should have, if time permits | Sections 2.9, 5.2 |
| Label-noise analysis (cleanlab) | Separate label errors from model errors | Optional extension | Sections 1.4, 1.5 |
| MLflow | Record and compare experiments | Core. Logging starts on the first run | Sections 2.4, 5.3 |
| Transformer (DistilBERT) | Compare against the TF-IDF baseline | Optional extension after the core is complete | Section 1.5 |

The literature supports these techniques as reasonable starting points. It does not establish in advance which model, threshold, or configuration will perform best on the selected dataset. Those decisions will be made from the project's own experimental results.

## 7.4 Feedback and Evaluation

The lecturer gave positive initial feedback and indicated that the project idea is good. This supports proceeding with the proposed direction. The table records what has and has not been received so that the document does not claim more than the team knows.

| Item | Status |
| --- | --- |
| Initial feedback on the project idea | Received. Positive; the idea was described as good. |
| Detailed written evaluation or technical recommendations | Not provided so far. |
| Official grading rubric and mark weights | Not provided so far. Section 7.6 is a proposed internal checklist until the rubric is available. |
| Required citation style | Not yet confirmed. References in Section 7.9 must be checked against it before submission. |
| Proposed next step | The team leader asks the lecturer for the official rubric and citation style, and Sections 7.6 and 7.9 are updated when they arrive. |

Until then, the project is assessed against its own objectives (Section 1.3), which are used as the technical evaluation dimensions:

- Correct implementation of ticket text classification.

- A fair comparison of the selected models, using Macro F1-score and class-level metrics.

- Analysis of class imbalance and of misclassified tickets.

- Implementation and evaluation of confidence-aware routing, including coverage and routing errors.

- Documentation of experiments, limitations, and final results.

These are the project's own evaluation dimensions. They are not marks that the lecturer has already assigned.

## 7.5 Suggested Improvements

The following improvements are based on the project scope, the dataset findings in Section 1.4, and the techniques reviewed above. Owners follow the proposed work breakdown (Section 2.6) and are confirmed at the System Design milestone.

| ID | Improvement | Reason and expected benefit | Priority | Proposed owner |
| --- | --- | --- | --- | --- |
| SI-1 | Establish a reliable baseline first | Use one fixed split and comparable preprocessing for DummyClassifier, Naive Bayes, and Logistic Regression. Gives a clear reference for every later change. | Core | Ahmed Fares |
| SI-2 | Address class imbalance | Report per-class precision, recall, and F1. Compare class_weight="balanced" with no weighting. Shows how the smallest queues behave (risk R1). | Core | Ahmed Fares |
| SI-3 | Treat the threshold as an experiment | Compare coverage and error at several thresholds on validation data, then report once on the test set. Evidence of the coverage-error trade-off (risks R5, R6). | Core | Abanoub |
| SI-4 | Analyze errors and label noise | Inspect the confusion matrix and misclassified tickets, and group the errors by pattern. Explains limits and separates label problems from model problems (risk R9). | Core | Sama |
| SI-5 | Track every experiment from the first run | Log parameters, metrics, and artifacts in MLflow starting November 7. Easier comparison and reproducibility (risk R10). | Core | Youssef |
| SI-6 | Check probability calibration | Draw a reliability diagram and compute ECE before and after calibration. Shows whether confidence can be trusted (risk R5). | Should have | Abanoub, Ahmed Fares |
| SI-7 | Optional enhancements | Streamlit demo, DistilBERT comparison, cleanlab, and SHAP or LIME. Richer demonstration, but only after the core works. | Optional | Ahmed Ashraf and others |

Cut-off rule for optional work. Optional items start only after the routing evaluation is complete (November 24) and stop at the November 27 cut-off in the schedule (Section 2.4). The core deliverables are a working classifier, a validated threshold, a human-review path, and an honest evaluation report. Optional work is dropped first if time runs short (risk R7).

## 7.6 Final Grading Criteria

The official grading weights have not been provided, so this section does not assign any marks. The table is a proposed internal quality checklist built from the four areas in the project outline (documentation, implementation, testing, and presentation) plus model evaluation, experiment tracking, and team contribution, which are specific to this project. The last column is left open so that the official weights can be entered when the lecturer provides the rubric.

| Evaluation area | Proposed assessment criteria | Evidence or deliverable | Official weight |
| --- | --- | --- | --- |
| Documentation | Clear problem statement, objectives, methodology, requirements, results, limitations, and references | Final technical report and this planning document (deliverables 1, 2, 3, 13) | Pending rubric |
| Implementation | Correct preprocessing, TF-IDF, classification, confidence-aware routing, and human-review path | Source code in the GitHub repository and the working prototype (deliverables 6, 7, 9, 12) | Pending rubric |
| Model evaluation | Correct data splitting without leakage, fair model comparison, suitable metrics, class-level analysis, honest reporting | Evaluation tables, classification report, confusion matrix, error analysis (deliverable 8) | Pending rubric |
| Testing | Tests for valid input, empty or invalid input, prediction output, threshold boundary, and routing status | Test cases and test report | Pending rubric |
| Experiment tracking | Parameters, metrics, and artifacts recorded and comparable | MLflow experiment records (deliverable 10) | Pending rubric |
| Presentation and demonstration | Clear explanation of the problem, method, architecture, results, and limitations, plus a demonstration of the workflow | Final presentation and a live or recorded demo (deliverables 11, 13) | Pending rubric |
| Team contribution and delivery | Assigned tasks completed and milestones met | Task records, GitHub history, milestone reviews | Pending rubric |

The final grade is determined by the lecturer's official rubric. Until it is available, this table is a checklist and not a mark distribution.

## 7.7 Limitations of the Review and of the Approach

- Synthetic data. The dataset is synthetic. Strong results on it would not by themselves show the same performance in a real company.

- Class imbalance and small test counts. Departments with few tickets have unstable per-class results, even with cross-validation.

- Confidence is not correctness. A high model score does not guarantee that a prediction is right, and some models (for example Naive Bayes) produce poorly calibrated probabilities.

- Label noise and overlapping queues. Some errors may come from the labels and not from the model.

- English only. The prototype is built for English tickets. German tickets are future work.

- Prototype scope. The system is not a production support platform and cannot guarantee error-free routing.

- Review scope. This is a focused, applied review of the techniques the project needs, written to guide design decisions. It is not an exhaustive survey of the literature.

## 7.8 Conclusion of the Literature Review

The reviewed techniques give TriageAI a practical foundation. TF-IDF with traditional classifiers is a manageable and interpretable starting point, and Macro F1-score with class-level metrics is a more honest measure than accuracy under class imbalance. Confidence-aware routing goes beyond basic classification by adding a decision rule for uncertain predictions, and calibration checks, error analysis, and MLflow tracking make that rule testable and reproducible. The next section turns these findings into stakeholder needs, user stories, use cases, and functional and non-functional requirements.

## 7.9 References

[1] Scikit-learn Developers. Working With Text Data; Classification of Text Documents Using Sparse Features; Probability Calibration. Scikit-learn documentation.

[2] Pedregosa, F., et al. (2011). Scikit-learn: Machine Learning in Python. Journal of Machine Learning Research, 12, 2825-2830.

[3] Salton, G., & Buckley, C. (1988). Term-weighting approaches in automatic text retrieval. Information Processing & Management, 24(5), 513-523.

[4] Manning, C. D., Raghavan, P., & Schütze, H. (2008). Introduction to Information Retrieval. Cambridge University Press.

[5] McCallum, A., & Nigam, K. (1998). A comparison of event models for Naive Bayes text classification. AAAI-98 Workshop on Learning for Text Categorization.

[6] Niculescu-Mizil, A., & Caruana, R. (2005). Predicting good probabilities with supervised learning. Proceedings of the 22nd International Conference on Machine Learning (ICML), 625-632.

[7] Devlin, J., Chang, M.-W., Lee, K., & Toutanova, K. (2019). BERT: Pre-training of deep bidirectional transformers for language understanding. Proceedings of NAACL-HLT, 4171-4186.

[8] Sanh, V., Debut, L., Chaumond, J., & Wolf, T. (2019). DistilBERT, a distilled version of BERT: smaller, faster, cheaper and lighter. arXiv:1910.01108.

[9] Sokolova, M., & Lapalme, G. (2009). A systematic analysis of performance measures for classification tasks. Information Processing & Management, 45(4), 427-437.

[10] El-Yaniv, R., & Wiener, Y. (2010). On the foundations of noise-free selective classification. Journal of Machine Learning Research, 11, 1605-1641.

[11] Geifman, Y., & El-Yaniv, R. (2017). Selective classification for deep neural networks. Advances in Neural Information Processing Systems 30 (NeurIPS).

[12] Pugnana, A., & Ruggieri, S. (2023). AUC-based selective classification. Proceedings of the 26th International Conference on Artificial Intelligence and Statistics, PMLR 206, 2494-2514.

[13] Guo, C., Pleiss, G., Sun, Y., & Weinberger, K. Q. (2017). On calibration of modern neural networks. Proceedings of the 34th International Conference on Machine Learning, PMLR 70, 1321-1330.

[14] Northcutt, C., Jiang, L., & Chuang, I. (2021). Confident learning: Estimating uncertainty in dataset labels. Journal of Artificial Intelligence Research, 70, 1373-1411.

[15] Zaharia, M., et al. (2018). Accelerating the machine learning lifecycle with MLflow. IEEE Data Engineering Bulletin, 41(4), 39-45. Also: MLflow Tracking documentation.

[16] Bueck, T. (Softoft). Customer IT Support - Ticket Dataset. Kaggle. Licensed under CC BY 4.0.

The team must verify each reference against its source and follow the lecturer's required citation style before final submission.

# 8. Requirements Gathering

## 8.1 Introduction

Requirements gathering identifies the people who interact with a system, understands what they need, and turns those needs into clear, testable requirements. For TriageAI it defines how a ticket is submitted, classified, evaluated, and then either marked as eligible for automatic routing or flagged for human review.

The requirements are based on the approved proposal (Section 1), the evaluation protocol (Section 2.9), the risk register (Section 4), and the KPIs (Section 5). Priorities follow the MoSCoW scheme (Must, Should, Could, Won't for this version). Numeric targets in this section are provisional planning targets and are confirmed after the baseline experiments. They are not claims about current performance. Optional features are marked separately so that they do not become mandatory without a team decision.

## 8.2 Stakeholder Analysis

Stakeholders are the people or groups who use the system, manage it, build it, or are affected by its output.

| Stakeholder | Role | Main needs and expectations | How TriageAI supports them |
| --- | --- | --- | --- |
| Customer | Submits a support request | The request reaches the appropriate department | The prototype classifies the submitted ticket text |
| Support agent | Handles tickets | A predicted department and information about how reliable the prediction is | Shows the predicted queue, the confidence score, and the routing status |
| Human reviewer | Reviews uncertain predictions | To see ambiguous tickets, understand the model's doubt, and confirm or correct the category | Flags low-confidence tickets and shows the top-two candidate queues |
| Support team leader | Oversees ticket distribution | Evidence that tickets go to the right place and that routing errors can be measured | Routing evaluation reports coverage, error rate, and human-review rate |
| Project team (six members) | Builds and evaluates TriageAI | Clear requirements, reproducible experiments, measurable results, manageable tasks | Evaluation protocol, MLflow tracking, traceability matrix (Section 8.9) |
| Demo operator | Runs the prototype | A predictable workflow and clear handling of bad input or missing files | Input validation and clear error messages |
| Lecturer or evaluator | Assesses the project | Correct methodology, honest results, clear documentation, and a working demonstration | Documentation, test report, evaluation results, and the final presentation |

Scope clarification. Customer submission, agent interaction, reviewer actions, and administration describe the intended workflow. The project does not build a complete customer portal, a production ticketing platform, or an administration system. The interface only needs to demonstrate the core prototype.

## 8.3 User Stories

Each user story states a need from the point of view of a stakeholder and lists acceptance criteria that can be checked.

| ID | User story | Acceptance criteria | Priority |
| --- | --- | --- | --- |
| US-01 | Submit a ticket. As a customer or demo user, I want to submit a ticket with a subject and a message so that the system can identify the most appropriate department. | The body text is required and the subject is optional (a missing subject is treated as an empty string, as in the dataset). A body that is empty or contains only whitespace produces a clear error message. A valid ticket is passed to the classification component. | Must |
| US-02 | View the predicted department. As a support agent, I want to see the predicted department so that I know where the ticket should be handled. | The prediction is one of the ten supported queues. The prediction is displayed clearly and linked to the submitted ticket. | Must |
| US-03 | View the confidence. As a support agent, I want to see the confidence score so that I understand how strongly the model favors its prediction. | The score of the predicted class is displayed. The interface states that the score is a model output and not a guarantee of correctness. | Must |
| US-04 | Route a confident ticket. As a support team leader, I want tickets at or above the configured threshold to be marked as eligible for automatic routing so that confident predictions are processed efficiently. | The score is compared with the configured threshold. A score equal to or above the threshold gives the status "eligible for automatic routing". The decision can be inspected during the demonstration. | Must |
| US-05 | Review an uncertain ticket. As a human reviewer, I want uncertain tickets flagged for review so that questionable predictions are not accepted automatically. | A score below the threshold gives the status "human review". The predicted queue and score are displayed. The top-two candidate queues are displayed when this feature is implemented. | Must |
| US-06 | Confirm or correct a prediction. As a human reviewer, I want to confirm or correct the suggested department so that the ticket receives a human-verified category. | If the review interface is built, the reviewer can pick a corrected queue from the ten supported queues. The model's original prediction is kept separate from the reviewer's decision. Saving corrections for retraining is an optional extension. | Should |
| US-07 | Evaluate the models. As a project team member, I want to evaluate candidate models with suitable metrics so that I can compare them and understand their weaknesses. | Models are evaluated on the defined validation set, with stratified 5-fold cross-validation and a single final test evaluation. Macro F1-score, per-class metrics, top-2 accuracy, and a confusion matrix are produced. Main misclassification patterns are recorded. | Must |
| US-08 | Evaluate routing. As a support team leader or evaluator, I want to know how many tickets are routed automatically and how often those are wrong so that I can judge the trade-off. | Coverage, error rate among routed tickets, and human-review rate are calculated at several thresholds. The threshold is chosen on validation data and the test set is used only for the final report. | Must |
| US-09 | Compare experiments. As a project team member, I want to record and compare experiments so that the best configuration can be identified and reproduced. | Parameters, metrics, and artifacts are logged in MLflow from the first run. Runs can be compared and the selected configuration can be re-run from its record. | Must |

## 8.4 Use Cases

### 8.4.1 Primary Use Case: Classify and Route a Support Ticket

| Use case ID and name | UC-01: Classify and Route a Support Ticket |
| --- | --- |
| Primary actor | Support agent or demo user |
| Supporting actor | Human reviewer |
| Goal | Obtain a predicted department and decide whether the ticket is eligible for automatic routing or needs human review. |
| Preconditions | The classification pipeline has been trained and saved. The ten supported queues are defined. The confidence threshold has been selected on validation data and is available in the configuration. The submitted ticket contains usable text. |
| Main success scenario | 1. The user submits a ticket subject and message. 2. The system validates the input. 3. The system combines subject and body and applies the same preprocessing used in training. 4. The fitted TF-IDF vectorizer transforms the text. 5. The trained classifier predicts a queue and returns class probabilities. 6. The system takes the probability of the predicted class as the confidence score. 7. The routing component compares the score with the configured threshold. 8. If the score is equal to or above the threshold, the ticket is marked as eligible for automatic routing. 9. The system displays the predicted queue, the confidence score, and the routing status. |
| Alternative A: low confidence | At step 8 the score is below the threshold. The ticket is flagged for human review. The predicted queue and score are displayed, together with the top-two candidate queues if implemented. A reviewer inspects the ticket and decides the department. |
| Alternative B: invalid input | At step 2 the body is empty or whitespace only. The system shows a clear validation message and does not run the classifier. |
| Alternative C: missing model files | At startup or at step 4 the saved pipeline or threshold configuration cannot be loaded. The system shows a clear error message that names the missing component and does not return a prediction. |
| Postconditions | A valid ticket has a predicted queue, a confidence score, and a routing status. A low-confidence ticket is identified for human review. The outcome can be inspected during evaluation or the demonstration. |
| Scope limitation | Marking a ticket as "eligible for automatic routing" does not connect to a real ticketing system. External routing is outside the project scope. |

### 8.4.2 Supporting Use Cases

| ID | Name | Primary actor | Description |
| --- | --- | --- | --- |
| UC-02 | Validate ticket input | Demo user | Checks that the ticket contains usable body text and rejects empty input with a clear message |
| UC-03 | Display classification result | Support agent | Shows the predicted queue, the confidence score, and the routing status |
| UC-04 | Review uncertain ticket | Human reviewer | Inspects a ticket whose score is below the threshold, with the top-two candidates |
| UC-05 | Correct ticket category | Human reviewer | Selects a corrected queue if the review feature is implemented |
| UC-06 | Evaluate classification models | Project team | Computes metrics, runs cross-validation, and inspects errors |
| UC-07 | Evaluate routing threshold | Project team | Measures coverage, routing errors, and human-review rate for candidate thresholds |
| UC-08 | Track model experiments | Project team | Records configurations and results in MLflow |

## 8.5 Functional Requirements

Functional requirements describe what the system must do. Priorities follow Section 8.1.

| ID | Requirement | Priority | Verification method | Traces to |
| --- | --- | --- | --- | --- |
| FR-01 | The system shall accept a ticket subject (optional) and body (required) as text. | Must | Submit valid tickets with and without a subject | US-01 |
| FR-02 | The system shall validate the input and show a clear message when the body is empty or whitespace only. | Must | Test empty, whitespace-only, and very long input | US-01, UC-02 |
| FR-03 | The system shall apply the same preprocessing at inference as in training, through one saved scikit-learn Pipeline. | Must | Check that inference uses the saved pipeline and not a separate copy of the steps | US-01, US-02 |
| FR-04 | The system shall transform the text with a TF-IDF vectorizer fitted on training data only. | Must | Review the pipeline code and the split order | US-07, NFR-09 |
| FR-05 | The system shall classify a valid ticket into one of the ten supported queues. | Must | Predict on valid examples and check that each label is in the supported set | US-02 |
| FR-06 | The system shall return class probabilities and the confidence score of the predicted class. | Must | Check that every result contains the score and that probabilities sum to 1 | US-03 |
| FR-07 | The system shall read the confidence threshold from a configuration value and not from a constant in the code. | Must | Change the value and confirm the routing behavior changes | US-04 |
| FR-08 | The system shall mark a prediction with a score equal to or above the threshold as eligible for automatic routing. | Must | Test scores below, exactly at, and above the threshold | US-04 |
| FR-09 | The system shall flag a prediction with a score below the threshold for human review. | Must | Test low-confidence predictions | US-05 |
| FR-10 | The system shall display the top-two candidate queues for tickets flagged for review. | Should | Check the ranking and displayed output | US-05 |
| FR-11 | The system shall let a reviewer confirm or correct the predicted queue and keep the original prediction separate. | Should | Complete a review scenario and inspect the stored decision | US-06 |
| FR-12 | The project shall evaluate models with Accuracy, Macro and Weighted F1, per-class precision and recall, top-2 accuracy, and a confusion matrix. | Must | Inspect the evaluation outputs | US-07, UC-06 |
| FR-13 | The project shall run stratified 5-fold cross-validation and report a majority-class reference model (DummyClassifier). | Must | Inspect the cross-validation results and the reference score | US-07 |
| FR-14 | The project shall measure automatic-routing coverage, error rate among routed tickets, and human-review rate at several thresholds, and show the coverage-accuracy curve. | Must | Inspect the routing evaluation report | US-08, UC-07 |
| FR-15 | The project shall log parameters, metrics, and artifacts of each experiment in MLflow from the first run. | Must | Inspect the MLflow records and re-run one logged configuration | US-09, UC-08 |
| FR-16 | The project shall produce a reliability diagram and Expected Calibration Error before and after calibration, if time permits. | Should | Inspect the calibration report | US-03, US-08 |
| FR-17 | The project shall provide an interactive demonstration interface (Streamlit) showing queue, confidence, and routing status, if time permits. | Should | Demonstrate the workflow | US-02 to US-05 |
| FR-18 | The system shall load the saved pipeline, the label list, and the threshold configuration at startup and report clearly if any is missing. | Must | Remove each file in turn and check the message | UC-01 (Alt. C), NFR-08 |

### 8.5.1 Core Processing Workflow

Ticket input → Input validation → Text preprocessing → TF-IDF transformation → Model prediction → Confidence evaluation → Routing decision

- Confidence score ≥ threshold: the prediction is marked as eligible for automatic routing.

- Confidence score < threshold: the ticket is flagged for human review.

The threshold is selected on validation data, and the final performance and coverage are measured on the held-out test set. The prototype displays the predicted department, the confidence score, and the resulting status so that the decision is easy to understand.

## 8.6 Non-Functional Requirements

Non-functional requirements describe quality attributes. Numeric values are provisional targets. They are confirmed after the baseline experiments (about November 13) and are consistent with the KPIs in Section 5.

| ID | Category | Requirement and provisional target | Verification method |
| --- | --- | --- | --- |
| NFR-01 | Performance | A single ticket is processed, including preprocessing, prediction, and the routing decision, in under 1 second on the team's laptops (the KPI in Section 5.3). Model loading time is excluded. | Time at least 100 representative tickets and report the mean and the 95th percentile |
| NFR-02 | Reliability | No tested input causes an unhandled error. Empty, whitespace-only, very long (over 10,000 characters), special-character, and non-English inputs each produce either a prediction or a clear message. | Run an input test suite |
| NFR-03 | Usability | One result view shows the predicted queue, the confidence score, and the routing status. | Informal walkthrough with classmates or instructors |
| NFR-04 | Maintainability | Preprocessing, modeling, routing, evaluation, and interface code are in separate modules, documented in a README, and merged through reviewed pull requests. | Review the repository structure and pull-request history |
| NFR-05 | Reproducibility | Random seed 42, package versions, and the dataset version are recorded. A logged run can be repeated and gives the same split and the same validation metrics for deterministic models. | Re-run one logged experiment and compare with MLflow |
| NFR-06 | Security and privacy | Only the synthetic public dataset is used. No real customer data, credentials, or full ticket texts are written to logs or committed to the repository. | Review the repository, logs, and demo data |
| NFR-07 | Scalability | The pipeline can score the full test set (about 2,451 tickets) in one batch run without errors or redesign, and the batch time is reported. | Run a batch prediction on the test set |
| NFR-08 | Fault handling | If the model file, label list, or threshold configuration is missing, the system shows a message that names it and does not return a prediction. | Simulate each failure |
| NFR-09 | Evaluation integrity | Model choice and threshold choice use training and validation data only. The test set is used once, for the final report. Test labels are never altered. | Review the code and the experiment log |
| NFR-10 | Transparency | The interface and the report state that the confidence score is a model output and not a guarantee, and that results come from synthetic data. | Inspect the interface and the report |
| NFR-11 | Portability | The project runs on a standard laptop with the documented Python version and no GPU. | Install from the README on a clean environment |
| NFR-12 | Model quality | The selected model must beat the majority-class reference on Macro F1-score. A numeric Macro F1 target and a target accuracy for automatically routed tickets (for example 95%) are agreed after the baseline results, and the achieved coverage is reported even when it is low. | Compare validation and test results with the agreed targets |

## 8.7 Data and Model Requirements

| Item | Requirement |
| --- | --- |
| Dataset | Customer IT Support - Ticket Dataset (Tobias Bueck, Softoft), Kaggle, CC BY 4.0. The file contains 28,587 rows and 16 columns. The data is synthetic, and every report must say so. |
| Working subset | The 16,338 English tickets. The 12,249 German tickets are excluded from this version. |
| Input features | The subject and body, joined into one text field. A missing subject (about 13% of rows) is replaced with an empty string. The body has no missing values. |
| Target | The queue column, with ten classes and no missing values. The same label list is used in training, evaluation, and prediction. |
| Excluded columns | answer, type, priority, tag_1 to tag_8, and version. The first ones are written or assigned after the ticket is handled and would leak information, and version is irrelevant. The exclusion stays unless a change is documented and justified. |
| Data checks | Duplicate texts, conflicting labels, text length, and non-English text were examined in Phase 1 (0 duplicates and 0 conflicting labels in the English subset) and are re-verified during EDA. |
| Split | 70% training, 15% validation, 15% test, stratified by queue, random seed 42. The test set has about 2,451 tickets. |
| Pipeline | Preprocessing, TF-IDF vectorizer, and classifier in one scikit-learn Pipeline, fitted on training data only. |
| Models | DummyClassifier (reference), Multinomial Naive Bayes, and Logistic Regression, each with and without class_weight="balanced". DistilBERT is an optional extension. |
| Model selection | Validation Macro F1-score as the primary metric, with stratified 5-fold cross-validation for stability. The test set is evaluated once. |
| Threshold | Selected on the validation set from predicted class probabilities, using a stated target, then evaluated on the test set. |
| Calibration (if time permits) | CalibratedClassifierCV fitted with cross-validation on training data, compared by reliability diagram and ECE. |
| Saved artifacts | The fitted pipeline, the label list, and the threshold configuration, saved with a recorded version and logged in MLflow. |
| Language | English only. |

## 8.8 Requirements Prioritization

| Priority | Requirements | Rationale |
| --- | --- | --- |
| Must have | Input validation, preprocessing, TF-IDF, model training and comparison, classification with probabilities, configurable threshold, review status, evaluation metrics, cross-validation, routing metrics, MLflow tracking, model loading with clear errors, and documentation (FR-01 to FR-09, FR-12 to FR-15, FR-18) | These are the core project objectives and the critical path (Section 2.5) |
| Should have | Top-two candidates, reviewer correction, calibration diagnostics, and Streamlit demo (FR-10, FR-11, FR-16, FR-17) | They improve the demonstration and the trust analysis but are dropped first if time runs short |
| Could have | Cleanlab label-noise analysis, SHAP or LIME explanations, DistilBERT comparison | Optional extensions after the core system works |
| Won't have (this version) | Production ticketing integration, multilingual classification, automatic customer replies, retraining from reviewer corrections, monitoring | Outside the scope in Section 1.5 |

The final set of delivered features is documented honestly. A feature is not reported as implemented only because it appears in this list.

## 8.9 Requirements Traceability

The matrix links each user story to its use cases, requirements, and the evidence that will show it is met. It will be completed with test case IDs during implementation.

| User story | Use case | Functional requirements | Evidence | Proposed owner |
| --- | --- | --- | --- | --- |
| US-01 | UC-01, UC-02 | FR-01, FR-02, FR-03 | Input validation test results | Sama |
| US-02 | UC-01, UC-03 | FR-03, FR-05 | Prediction tests on valid examples | Ahmed Fares |
| US-03 | UC-03 | FR-06, FR-16 | Interface check, calibration report | Abanoub |
| US-04 | UC-01 | FR-07, FR-08 | Threshold boundary tests | Abanoub |
| US-05 | UC-04 | FR-09, FR-10 | Low-confidence and top-two tests | Abanoub |
| US-06 | UC-05 | FR-11 | Review scenario (if implemented) | Ahmed Ashraf |
| US-07 | UC-06 | FR-04, FR-12, FR-13 | Evaluation report and error analysis | Ahmed Fares, Sama |
| US-08 | UC-07 | FR-14 | Routing evaluation report | Abanoub |
| US-09 | UC-08 | FR-15 | MLflow experiment records | Youssef |

## 8.10 Requirements Acceptance Criteria

The requirements are considered sufficiently implemented for the final prototype when the team can show that:

- A valid ticket is processed, and an invalid ticket produces a clear message.

- The model predicts one of the ten supported queues, and the predicted queue, confidence score, and routing status are displayed.

- The configured threshold decides the routing status correctly, including at the boundary value.

- Low-confidence predictions are flagged for human review.

- Models are compared on validation data and a majority-class reference, with Macro F1-score, per-class metrics, and cross-validation.

- Final performance is measured once on the held-out test set with the agreed metrics.

- Routing coverage, error rate among routed tickets, and human-review rate are measured at several thresholds.

- Experiments and their configurations are recorded in MLflow and can be repeated.

- Invalid inputs and known failure cases are tested, and the results are documented.

- The final report explains the method, results, limitations (including the synthetic data), and future improvements.

## 8.11 Conclusion of Requirements Gathering

The stakeholder analysis, user stories, and use cases describe how a ticket moves through classification and routing. The functional and non-functional requirements define what the prototype must do and how well, with provisional targets that are confirmed after the baseline. The traceability matrix connects every need to evidence. The next step is System Analysis and Design (deadline November 6, 2026), which covers the architecture, component responsibilities, data flow, model integration, routing logic, and testing strategy.

# 9. Conclusion

TriageAI aims to improve the first handling of customer support tickets through NLP classification and confidence-aware routing. By combining traditional ML models with a human-in-the-loop decision, the project investigates not only whether a ticket can be classified, but also whether the system should route it automatically or ask a person to review it.

The plan puts a reproducible baseline, careful evaluation, and a measurable routing mechanism first, and leaves optional enhancements such as a Transformer comparison, Explainable AI, and monitoring for future work.

## Dataset citation

Bueck, T. (Softoft). Customer IT Support - Ticket Dataset. Kaggle, licensed under CC BY 4.0. https://www.kaggle.com/datasets/tobiasbueck/multilingual-customer-support-tickets